## Workplan template
2022
| Mar | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jul | Aug
Milestones
Data gathering?
Data cleaning?
Developing your system?
Proofreading?
Submission?
Viva and going to the pub to celebrate?
Writing
Project description | 2022 Mar: 28
2022
| Mar | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jul | Aug

## Example workplan
Student name: Someone who passed Stage 1, has written most of chapters 2-5, and has 1 study left to do
Topic/ title: Really interesting PhD
| 2016 | [7 empty] | 2017 | [11 empty] | 2018
Activity | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Studies
Design final study
Build prototype for final study
Recruit participants
Run final study
Analyse data from final study
Prepare Stage 2 document
Thesis writing
Write Chapter 6
Write Chapter 7
Write Chapter 8
Write Introduction
Revise whole thesis to bring together
Paper writing
Write CHI 2017 paper
Revise CHI 2017 paper
Prepare for CHI 2017
CHI 2017
Holidays
Milestones/ Deliverables
Stage 2 |  |  |  |  | *
CHI 2017 deadline |  |  |  |  | *
First full draft of thesis | [10 empty] | *
Select examiners | [10 empty] | *
Submit thesis | [14 empty] | *
PhD Exam | [16 empty] | *